## Sheet1
SPRINT -1
USER STORY | TO DO | IN PROGRESS | IMPEDIMENT | TO VERIFY | DONE
1.SIGNUP module,Compare items, add products into wishlist [Matte Soumya Reddy] | Database design,registration pages, |  | integrating user module | Routing of all login to particular profile. | 1. Registration page for user and retailer. 2. Encrypting the password.
2.Admin Module-login,retailer approval, view all products, sorting and filtering the products[Varad Nilesh Suryawanshi] | Admin module,User module |  | integrating user module | approval of retailer,filtering of products | 1. Admin login and retailer approval.
3.Login Module[user,retailer],forget password by generating OTP,Cart Module-adding into cart and removing from cart,update the quantity of the product using plus minus signs which will auto-update the price.[Kirti Barapatre] | 3 Module Login, User module |  | integrating user module | login with particular user and create a session,otp verfication | 1. Login pages for user and retailer 2. Forget password module with Otp generation
4.Retailer Module-Display Retailer details, Searching Products and User Dashboard and orders dashboard [Ashwin D] | Retailer module,User module |  | integrating user module | display retailer details,display user and order details | 1. Display the retailer details 2. Searching the products
SPRINT -2
1.SIGNUP module,Compare items, add products into wishlist [Matte Soumya Reddy] | Add products into the compare list and wish list. |  |  |  | All Registration Module done for three users. And Completed module of user wishlist by adding products
2.Admin Module-login,retailer approval, view all products, sorting and filtering the products[Varad Nilesh Suryawanshi] | Sorting the products Filtering the Products |  |  |  | Completed Admin module.Worked with retailer approval module.work with sorting and filtering of products in user module and completed all.
3.Login Module[user,retailer],forget password by generating OTP,Cart Module-adding into cart and removing from cart,update the quantity of the product using plus minus signs which will auto-update the price.[Kirti Barapatre] | Adding and removing products from Cart Update Products using signs in cart and auto update the price. |  |  |  | Login module completed and work with otp functions for forget password.worked with adding products into cart and updation of cart
4.Retailer Module-Display Retailer details, Searching Products and User Dashboard and orders dashboard [Ashwin D] | Display User details Orders dashboards. |  |  |  | Worked with retailer module and displaying the details of the module.sending request to admin for approval.worked with user dashboard,order dashboard and completed it.